## Sheet1
| Product Name |  | Apon Bazaar |  | TC Start Date |  | 2024-11-24 |  | TEST CASE SUMMARY |  |  | Out of Scope | Issue
| Module Name |  | All |  | TC End Date |  | 2024-05-12 |  | PASS | 4
[5 empty] | Device Tested |  | ios |  | FAIL | 0
| Browser |  | microsoft edge, google chrome, firefox |  | Performance Tested |  |  |  | Out of scope | 0
| Test Case Developed & Executed By |  | Tanmoy Datta |  | Developer Name |  | shakib, Selim |  | Total | 4
Date | Module/Feature Name | Sub feature | Priority | Test Case ID | Test Cases | Test Type | Test Steps | Test Data | Screenshot | Expected Result | Actual Result | Status | Sprint | Task NO.
2024-05-12 | Registration | common OTP | High | TC_001 | Trying to set a common OTP code and register using a valid phone number. | Functional Testing | Open apon Bazaar app->Menu bar->Tab login->Registration->Enter Phone number->confrim mobile number->Enter OTP-> Next | Phone number: 01716948523 Common OTP Set: 2312 | https://prnt.sc/UQAFzhn4vzGa | OTP should be successfully received on the customer's phone number. | As Expected. | Pass
2024-05-12 | Registration | Uniqe OTP | High | TC_002 | Trying to set a Uniqe OTP code and register using a valid phone number. | Functional Testing | Open apon Bazaar app->Menu bar->Tab login->Registration->Enter Phone number->confrim mobile number->Enter OTP-> Next | Phone number: 01716948523 Uniqe OTP Set: 8826 | https://prnt.sc/b9A70PE5rntR | OTP should be successfully received on the customer's phone number. | As Expected. | Pass
2024-05-12 | Forgot Password | common OTP | High | TC_003 | Trying to set a common OTP code and Forgot password using a valid phone number. | Functional Testing | Open apon Bazaar app->Menu bar->Tab login->Forgot password ->Enter Phone number->Send OTP ->Enter OTP-> Next | Phone number: 01716948523 Common OTP Set: 9809 | https://prnt.sc/3Hd5oMISUb0j | OTP should be successfully received on the customer's phone number. | As Expected. | Pass
2024-05-12 | Forgot Password | Uniqe OTP | High | TC_004 | Trying to set a Uniqe OTP code and Forgot password using a valid phone number. | Functional Testing | Open apon Bazaar app->Menu bar->Tab login->Forgot password ->Enter Phone number->Send OTP ->Enter OTP-> Next | Phone number: 01716948523 Uniqe OTP Set: 6898 | https://prnt.sc/Ky7etex3CTpn | OTP should be successfully received on the customer's phone number. | As Expected. | Pass